## Sheet1
Fault No. | Date | Test No. | Error | Issued to | Date Retested | OK?
1 | 2014-03-17 | all | jQuery Mobile 1.4.1 has a syntax error on Android versions 2.x | Rob | 2014-03-19 | Yes
2 | 2014-03-17 | 9 | Conference dates are not formatted correctly | Paul | 2014-03-19 | Yes
3 | 2014-03-17 | 14 | Selectors don't meet standards | Paul | 2014-03-19 | Yes
4 | 2014-03-17 | 15 | Selectors don't meet standars | Paul | 2014-03-19 | Yes
5 | 2014-03-17 | 17 | Brackets don't follow K & R style | Paul | 2014-03-19 | Yes
6 | 2014-03-17 | 15 | Soft character width of 80 characters not observed | Paul | 2014-03-19 | Yes
7 | 2014-03-17 | 18 | Soft character width of 80 characters not observed | Paul | 2014-03-19 | Yes
8 | 2014-03-17 | 18 | Missing semicolon | Paul | 2014-03-19 | Yes
9 | 2014-03-17 | 2c, 3c, 4c | List view items have inconsistent spacing and shadow in API 16 | Rob | 2014-03-19 | Yes
10 | 2014-03-17 | 5 | HTML selector ID #feedbackHome-p has uppercase letter | Rob | 2014-03-20 | Yes
11 | 2014-03-17 | 8 | Javascript variables Start and End in routing.js are not camel case | Rob | 2014-03-19 | Yes
12 | 2014-04-28 | 33 | Indent level in helper.js file is four spaces not two | Rob | 2014-04-28 | Yes
13 | 2014-04-29 | 34 | downloadData function does not have JSDoc | Rob | 2014-04-28 | Yes
14 | 2014-06-10 | 65 | Webiste does not have pages for viewing, adding and editting Venues
15 | 2014-06-10 | 65 | `venue`.`Street` isn't large enough for sample address | Rob | 2014-06-10 | Yes
16 | 2014-06-10 | 65 | `conference`.`Token` isn't generated when adding a conference
17 | 2014-06-10 | 65 | Speaker cannot be added without Qualification
18 | 2014-06-10 | 65 | Speaker titles cannot include punctuation (Mr.)
19 | 2014-06-10 | 65 | Spekaer cannot be added without a bio
20 | 2014-06-10 | 65 | Speaker bio cannot contain certain punctuation
21 | 2014-06-10 | 65 | Text area on Speaker add page is the wrong size | Rob | 2014-06-10 | Yes
22 | 2014-06-10 | 65 | Conference drop down does not contain name | Rob | 2014-06-10 | Yes
23 | 2014-06-10 | 65 | Unknown column 'Polling_Available' when adding Session | Rob | 2014-06-10 | Yes
24 | 2014-06-10 | 65 | Sessions cannot be added without feedback
25 | 2014-06-10 | 65 | Sponsor decriptions are too limited. | Rob | 2014-06-10 | Yes
26 | 2014-06-10 | 65 | Sponsor images cannot be changed on edit
27 | 2014-06-10 | 65 | Uploaded images aren't moved to UPLOADED_FILES
28 | 2014-06-10 | 65 | Editting a conference doesn't prefil the venue correctly | Rob | 2014-06-10 | Yes
29 | 2014-06-10 | 65 | Website has no way to tie a sponsor to a conference
30 | 2014-06-10 | 65 | Website does not allow for adding a session without any presenters
31 | 2014-06-10 | 65 | Website does not allow feedback sections to be tied to conferences
32 | 2014-06-10 | 57 | Feedback question titles get truncated if too long | Rob | 2014-06-10 | Yes
33 | 2014-06-10 | 46 | Mobille application hangs if section has no sessions | Rob | 2014-06-10 | Yes
34 | 2014-06-10 | 62 | Transparent sponsor logos look bad
35 | 2014-06-10 | 52 | Q&A form doesn't always open | Rob | 2014-06-10 | Yes
36 | 2014-06-10 | 52,60,63,58 | Q&A and Polling pages don't always get unloaded from DOM
37 | 2014-06-10 | 46 | Previous button on schedule page doesn't always work. | Rob | 2014-06-11 | Yes
38 | 2014-06-10 | 57 | Web service throws an exception when handling OR questions | Rob | 2014-06-10 | Yes
39 | 2014-06-11 | 45 | App navigation panel sometimes doesn't open after opening app.
40 | 2014-06-11 | 46-53 | App fails to log onto conference on device API 10
41 | 2014-06-11 | 57 | Collapsible div does not close and open next div automatically