## Iteration 1
Team Name | Student Name
JPRS Squad
Project Manager/Test Manager | Rudhra
Systems Analyst | Shuhei Nakahodo
Architect | Paulo Goncalves
Assignment 1 - Elaboration Iteration - Due Week 3
Document / Deliverable | Sections / Task | Assigned To | Internal Date Due | Submitted On Time | State
Project Management | Initial Task List for this iteration (eMailed to teacher) | Rudhra | First Day of Iteration
| Completed Task List for this iteration (eMailed to teacher) | Rudhra | Last Day of Iteration
| Risk List - Include the 10 most serious risks to the project | All Team Members
| Research Cloud storage/version control options for group access, document and make selction | Rudhra
Interview Questions | Develop a set of questions for the client & provide written responses. | All Team members
Review Mechanism | Develop & document a review mechanism to ensure you have an accurate understanding | Rudhra
| Review the documentation & software to gain a sound understanding of the company & product | All Team members
Software Testing | Software Testing - Part 1 (to ensure the current programs have no faults & have good usability) | #REF!
| Software Testing - Part 2 (to ensure the current programs have no faults & have good usability) | Rudhra
| Software Testing - Part 3 (to ensure the current programs have no faults & have good usability) | Shuhei Nakahodo
| Software Testing - Part 4 (to ensure the current programs have no faults & have good usability) | Paulo Goncalves
Requirement Tracability Matrix | Update the last Requirements Tracability Matrix to ensure it is accurate | Shuhei Nakahodo
| Add any new features to the Requirements Tracibility Matrix | Paulo Goncalves
| Determine and document any additional features required by the client. (Vision, System Wide requirements etc)) | Shuhei Nakahodo
Analysis & Design Documents | Review the database design to ensure it supports the requirements (Update the Design) | Paulo Goncalves
| Update the Business Rules to ensure they are accurate | Shuhei Nakahodo
| Use Case specifications for Version 3 Functionality | #REF!
| Discuss with the client the requirement for Reports & Document those requirements | #REF!
| Review the Use Case Diagram to ensure it supports the requirements (Update the Diagram) | #REF!
Work Log | Log of all tasks completed by a team member this Iteration | All Team members
Testing Part 1
Enter the name of each use case the
functionality for which will be tested by
#REF!
in this iteration (enter in cells to the right)
Testing Part 2
Enter the name of each use case the
functionality for which will be tested by
Rudhra
in this iteration (enter in cells to the right)
Testing Part 3
Enter the name of each use case the
functionality for which will be tested by
Shuhei Nakahodo
in this iteration (enter in cells to the right)
Testing Part 4
Enter the name of each use case the
functionality for which will be tested by
Paulo Goncalves
in this iteration (enter in cells to the right)
Note on D11: Name of the Team member to whom the task has been assigned. Each task can only be assigned to 1 team member.
Note on E11: Completion date of this task -> with reference to the group timeline requirements
Note on F11: Was the Item submitted on time. (Yes or No)
Note on G11: Assigned, % Complete, Complete

## Iteration 2
| Team Name | Student Name
| JPRS Squad | JPRS Squad
| Project Manager/Test Manager | Rudhra
| Systems Analyst | Shuhei Nakahodo
| Architect | Paulo Goncalves
Assignment 2 - Construction 1 - Due Week 7
| Document / Deliverable | Sections / Task | Assigned To | Internal Date Due | State | Reference material | Paulo | Shuhei | Rudhra
| Project Management | Complete initial task assignments for the group, make the list available to team members and eMail it to the Teacher | Rudhra | First Day of Iteration | YES | 100%
|  | Finalize the Task List for this iteration and eMail it to the teacher | Rudhra | Last Day of Iteration
|  | Review and update the Risk List - Includes the 10 most serious risks to the project at this point in time | Paulo Goncalves
|  | Develop an Iteration plan for this iteration for Items 1 to 5 (eMail a copy to the Teacher) | Rudhra | Week 4 - Wednesday | YES | 100%
|  | Review the Iteration progress and complete - Item 6 (Assessment) | Paulo Goncalves
|  | Update the Project Gantt Chart with tracking data for project tasks & produce progress reports. | Shuhei Nakahodo
|  | Work log of all tasks completed by a team member this Iteration (eMail a PDF Version of the Worklog to the teacher) | Each Team Member
| Requirements | Use Case Specifications for the next iterations functionality | Shuhei Nakahodo
|  | Update the Traceability Matrix for all system requirements. | Shuhei Nakahodo
| Design documentation | Report designs for all reports you are developing this iteration (signed off by teacher before you commece developing them) | Each team Member | [5 empty] | YES
|  | Screen designs for all Screens you are developing this iteration (signed off by teacher before you commece developing them) | Each team Member | [5 empty] | YES
| Programming and Build | Updated Database Script - Ensure all records hold realistic data and allow all business rules to be tested. | Shuhei Nakahodo | Friday Week 5
|  | Programs to the value of 7 Points (see program allocation by Project Manager below) | Paulo Goncalves | Friday Week 6 | YES | 100%
|  | Programs to the value of 7 Points (see program allocation by Project Manager below) | Rudhra | Friday Week 6 | YES | 100%
|  | Programs to the value of 7 Points (see program allocation by Project Manager below) | Shuhei Nakahodo | Friday Week 6 | YES | 100%
|  | Debug application (based on test results) Each programmer to fix their own problems | Each Team Member | Wednesday Week 7 |  |  | No Bugs Reported | Bugs reported | No Bugs Reported
|  | Build & Build Documentation Mobile App & Web (Uniserver and Externally hosted Versions) | Paulo Goncalves
|  | Research the Deployment of the Mobile apps to Play store and App store & Liase with epworth Regarding the Developer accounts | Paulo Goncalves / Shuhei Nakahodo
| Test Solution | Develop test plans & test software developed by the Test Manager/Project Manager | Paulo Goncalves | Tuesday Week 7 | YES | 100%
|  | Develop test plans & test software developed by the Architect | Shuhei Nakahodo | Tuesday Week 7
|  | Develop test plans & test software developed by the Systems Analyst | Rudhra | Tuesday Week 7 | YES | 100% |  |  | YES
|  | Test program management including Test Summary, Fault Logs | Rudhra |  | YES | 100%
|  | User Acceptance Test for all functionality available in Week 7 | Rudhra |  | YES | 100%
| Use Case Specifications | Add Venue
Edit Venue
| Enter the names of the Uses Case | Delete Venue
| Specifications that will be developed by | View Venue
| Shuhei Nakahodo | Reset Password for login area
| in this iteration (enter in cells to the right) | Restricting only owner of the conference to edit/delete/view
Preparing specification for PDF reports
Preparing specification for help system
` | Programs Part 1 | Use Case Name | Program Complexity Level | Points
| Enter the name of each use case | List the Q & A questions for each session in the Conference | 1 | 1
| that will be implemented by | List the Q & A questions for the session | 1 | 1
| Paulo Goncalves | List the Feedback questions and a summary of the results of the feedback for each session in the Conferen | 1 | 1
| in this iteration (enter in cells to the right) | List the Feedback questions and a summary of the results of the feedback for each session in the session | 1 | 1
|  | List the Polling questions and a summary of the results of the feedback for each session in the Conference | 1 | 1
|  | List the Polling questions and a summary of the results of the polling for the session. | 1 | 1
|  | List the conference sections, session details and speakers. | 1 | 1
|  |  | Total points | 7
| Programs Part 2 | Use Case Name | Program Complexity Level | Points
| Enter the name of each use case | Review and fix fault reports | 4 | 3
| that will be implemented by | Conference Administrators gain access to their Conference data | 2 | 2
| Rudhra | All Web Pages must check that the user is logged on and authenticated. | 1 | 1
| in this iteration (enter in cells to the right) | Modify add/edit conference to link Feed back Form | 2 | 1.5
|  |  | Total points | 7.5
| Programs Part 3 | Use Case Name | Program Complexity Level | Points
|  | Add Venue | 1 | 1.5
| Enter the name of each use case | Edit Venue | 1 | 2
| that will be implemented by | Delete Venue | 1 | 1.5
| Shuhei Nakahodo | View Venue | 1 | 1
| in this iteration (enter in cells to the right) | Help system (Make help system to 1 or 2 areas) | 3 | 1.5
|  |  | Total points | 7.5
Note on D11: Name of the Team member to whom the task has been assigned. Each task can only be assigned to 1 team member.
Note on E11: Completion date of this task -> with reference to the group timeline requirements
Note on F11: Assigned, % Complete, Complete
Note on G11: The Name of the document or programs that contains this deliverable
Note on I11: Individual work assignments
Note on J11: Individual work assignments
Note on K11: Individual work assignments

## Iteration 3
| Team Name | Student Name
JPRS Squad
| Project Manager/Test Manager | Rudhra
| Systems Analyst | Shuhei Nakahodo
| Architect | Paulo Goncalves
Assignment 2 - Construction 1 - Due Week 11
| Document / Deliverable | Sections / Task | Assigned To | Internal Date Due | State | Reference material
| Project Management | Complete initial task assignments for the group, make the list available to team members and eMail it to the Teacher | Rudhra | First Day of Iteration
|  | Finalize the Task List for this iteration and eMail it to the teacher | Rudhra | Last Day of Iteration
|  | Review and update the Risk List - Includes the 10 most serious risks to the project at this point in time | Paulo Goncalves
|  | Develop an Iteration plan for this iteration for Items 1 to 5 (eMail a copy to the Teacher) | Rudhra
|  | Review the Iteration progress and complete - Item 6 (Assessment) | Shuhei Nakahodo | Week 4 - Wednesday
|  | Update the Project Gantt Chart with tracking data for project tasks & produce progress reports. | Paulo Goncalves
|  | Work log of all tasks completed by a team member this Iteration (eMail a PDF Version of the Worklog to the teacher) | All team members
| Requirements | Use Case Specifications for Version 4 functionality | Rudhra
|  | Update the Traceability Matrix for all system requirements. | Shuhei Nakahodo
| Design documentation | Report designs for all reports you are developing this iteration (signed off by teacher before you commece developing them) | Each team Member
|  | Screen designs for all Screens you are developing this iteration (signed off by teacher before you commece developing them) | Each team Member
| Programming and Build | Updated Database Script - Ensure all records hold realistic data and allow all business rules to be tested. | Shuhei Nakahodo | Monday Week 7
|  | Changes required due to user acceptance testing. Each developer to update their programs | All team members
|  | Programs to the value of 7 Points (see program allocation by Project Manager below) | Paulo Goncalves | Friday Week 6
|  | Programs to the value of 7 Points (see program allocation by Project Manager below) | Rudhra | Friday Week 6
|  | Programs to the value of 7 Points (see program allocation by Project Manager below) | Shuhei Nakahodo | Friday Week 6
|  | Debug application (based on test results) Each programmer to fix their own problems | All Members | Wednesday Week 7
|  | Build & Build Documentation Mobile App & Web (Uniserver and Externally hosted Versions) | Paulo Goncalves
|  | Liase with Epworth and organise the Developer Accounts for the Play store and App store & the web server setup (Document all these aspects) | Paulo Goncalves / Shuhei Nakahodo
| Test Solution | Develop test plans & test software developed by the Test Manager | Paulo Goncalves | Tuesday Week 7
|  | Develop test plans & test software developed by the Project Manager | Shuhei Nakahodo | Tuesday Week 7
|  | Develop test plans & test software developed by the Systems Analyst | Rudhra | Tuesday Week 7
|  | Load testing | All team members
|  | Test program management including Test Summary, Fault Logs | Rudhra
|  | User Acceptance Test - Version 3 | Shuhei Nakahodo
Use Case Specifications
Enter the names of the Uses Case
Specifications that will be developed by
Rudhra
in this iteration (enter in cells to the right)
` | Programs Part 1 | Use Case Name | Program Complexity Level | Points
| Enter the name of each use case | View all customers | 1 | 1 | Example only.
| that will be implemented by | Add New Subject | 2 | 1.5
| Paulo Goncalves | Update Customer details | 3 | 2
| in this iteration (enter in cells to the right) | Delete a Customer | 1 | 1
|  |  | Total points | 5.5
| Programs Part 2 | Use Case Name | Program Complexity Level | Points
Enter the name of each use case
that will be implemented by
Rudhra
in this iteration (enter in cells to the right)
|  |  | Total points | 0
| Programs Part 3 | Use Case Name | Program Complexity Level | Points
Enter the name of each use case
that will be implemented by
Shuhei Nakahodo
in this iteration (enter in cells to the right)
|  |  | Total points | 0
Note on D11: Name of the Team member to whom the task has been assigned. Each task can only be assigned to 1 team member.
Note on E11: Completion date of this task -> with reference to the group timeline requirements
Note on F11: Assigned, % Complete, Complete
Note on G11: The Name of the document or programs that contains this deliverable

## Iteration 4
Team Name | Student Name
JPRS Squad
Project Manager/Test Manager | Rudhra
Systems Analyst | Shuhei Nakahodo
Architect | Paulo Goncalves
Assignment 4 - Transition Iteration - Part 1 - Due week 14
Document / Deliverable | Sections / Task | Assigned To | Internal Date Due | State | Reference material
Project Management | Initial Task List for this iteration (eMailed to teacher) | Rudhra | First Day of Iteration
| Completed Task List for this iteration (eMailed to teacher) | Rudhra | Last Day of Iteration
| Updated Risk List that includes the 10 most serious risks to the project at this point | Shuhei Nakahodo
| Update the Project Gantt Chart with tracking data for project tasks & produce progress reports. | Rudhra
| Develop an Iteration plan for this iteration for Items 1 to 5 (eMail a copy to the Teacher) | Rudhra | Week 4 - Wednesday
| Review the Iteration progress and complete - Item 6 (Assessment) | Shuhei Nakahodo
Build and Programming | Changes required due to user acceptance testing. Each developer to update their programs | All Team members | Friday Week 11
| Finalise Any outstanding Programs | Paulo Goncalves | Friday Week 12
| Finalise Any outstanding Programs | Shuhei Nakahodo | Friday Week 12
| Finalise Any outstanding Programs | Rudhra | Friday Week 12
| Build & Build Documentation | Paulo Goncalves
| Finalize Test Summary & test pack | Rudhra
| Finalize Regression testing | All team members | Thursday Week 16
Documentation | Finalize the user tutorials | Paulo Goncalves | Friday Week 15
| Finalize & Publish Technical Manual | Rudhra | Friday Week 15
Deployment to Production Environment | Install/uninstall scripts and instructions (Task Asssignments - See below) | All Team Members | Week 13 - Monday
| Plan and perform software installation (See below) | Paulo Goncalves / Shuhei Nakahodo | Week 13 - Monday
| Deploy Database (as per the clients requirements) | Paulo Goncalves / Shuhei Nakahodo | Week 13 - Monday
| Arrange with Epworth the uploading of the web-site to its production location. | Paulo Goncalves / Shuhei Nakahodo
| Local and Externally hosted site setup with instructions | Paulo Goncalves / Shuhei Nakahodo | Week 13 - Monday
| Deploy Mobile apps to Play store and App store | Paulo Goncalves / Shuhei Nakahodo
Test Solution | Debug application (based on test results) Each programmer to fix their own problems | All team members | Wednesday Week 1
System Testing | System Testing - Part 1 Programs | Shuhei Nakahodo | Tuesday Week 12
| System Testing - Part 2 Programs | Rudhra | Tuesday Week 12
| Sign off of Final Version of User Acceptance Test | Rudhra | Friday Week 12
| Test program management including Test Summary, Fault Logs | Rudhra
Work Log | Log of all tasks completed by a team member this Iteration | All Team members
System Testing - Part 1
Enter the name of each use case that
will have system testing completed by
Shuhei Nakahodo
in the cells on the right.
System Testing - Part 2
Enter the name of each use case that
will have system testing completed by
Rudhra
in the cells on the right.
Note on D11: Name of the Team member to whom the task has been assigned. Each task can only be assigned to 1 team member.
Note on E11: Completion date of this task -> with reference to the group timeline requirements
Note on F11: Assigned, % Complete, Complete
Note on G11: The Name of the document or programs that contains this deliverable

## Iteration 5
Team Name | Student Name
JPRS Squad
Project Manager/Test Manager | Rudhra
Systems Analyst | Shuhei Nakahodo
Architect | Paulo Goncalves
Assignment 5 - Transition Iteration - Part 2 - Due week 16
Document / Deliverable | Sections / Task | Assigned To | Internal Date Due | State | Reference material
Project Management | Initial Task List for this iteration (eMailed to teacher) | Rudhra | First Day of Iteration
| Completed Task List for this iteration (eMailed to teacher) | Rudhra | Last Day of Iteration
| Updated Risk List that includes the 10 most serious risks to the project at this point | Rudhra
| Update the Project Gantt Chart with tracking data for project tasks & produce progress reports. | Shuhei Nakahodo
| Develop an Iteration plan for this iteration for Items 1 to 5 (eMail a copy to the Teacher) | Rudhra | Week 4 - Wednesday
| Review the Iteration progress and complete - Item 6 (Assessment) | Rudhra
Deployment | Complete Install Application on Clients Hardware (if necessary) | Paulo Goncalves / Shuhei Nakahodo | Tuesday Week 15
| Complete App deployment - If Required | Paulo Goncalves / Shuhei Nakahodo
| Train Client in the use of application ( see assignments below) | All Team Members | Friday Week 15
| Finalize Test Summary & test pack | Rudhra
Documentation | Finalize the Mobile App and Web based tutorials | Shuhei Nakahodo | Friday Week 15
| Deliverables Review | Rudhra
Presentation | Presentation of Final system | All team members | Various
Work Log | Log of all tasks completed by a team member this Iteration | All Team members
Note on D10: Name of the Team member to whom the task has been assigned. Each task can only be assigned to 1 team member.
Note on E10: Completion date of this task -> with reference to the group timeline requirements
Note on F10: Assigned, % Complete, Complete
Note on G10: The Name of the document or programs that contains this deliverable