## Sheet1
Fault No. | Date | Test No. | Error | Issued to | Date Retested | OK?
1 | 2014-03-17 | all | jQuery Mobile 1.4.1 has a syntax error on Android versions 2.x | Rob | 2014-03-19 | Yes
2 | 2014-03-17 | 9 | Conference dates are not formatted correctly | Paul | 2014-03-19 | Yes
3 | 2014-03-17 | 14 | Selectors don't meet standards | Paul | 2014-03-19 | Yes
4 | 2014-03-17 | 15 | Selectors don't meet standars | Paul | 2014-03-19 | Yes
5 | 2014-03-17 | 17 | Brackets don't follow K & R style | Paul | 2014-03-19 | Yes
6 | 2014-03-17 | 15 | Soft character width of 80 characters not observed | Paul | 2014-03-19 | Yes
7 | 2014-03-17 | 18 | Soft character width of 80 characters not observed | Paul | 2014-03-19 | Yes
8 | 2014-03-17 | 18 | Missing semicolon | Paul | 2014-03-19 | Yes
9 | 2014-03-17 | 2c, 3c, 4c | List view items have inconsistent spacing and shadow in API 16 | Rob | 2014-03-19 | Yes
10 | 2014-03-17 | 5 | HTML selector ID #feedbackHome-p has uppercase letter | Rob | 2014-03-20 | Yes
11 | 2014-03-17 | 8 | Javascript variables Start and End in routing.js are not camel case | Rob | 2014-03-19 | Yes
12 | 2014-04-28 | 33 | Indent level in helper.js file is four spaces not two | Rob | 2014-04-28 | Yes
13 | 2014-04-29 | 34 | downloadData function does not have JSDoc | Rob | 2014-04-28 | Yes