## Fault_Summary Semester 2
Fault Summary JPRS Squad 2014 BlackBox Testing Iteration 2
Date | Annex | Test No | Step No | Category | Descriptipn | Raised By | Issued to | Date Fixed | Status
2014-07-30 | A Home Page | 1 | 7 | Standards | Login user with a long name doesn’t display the logged user name properly. | Rudhra | Rudhra | 2014-08-16 | FIXED | fixed to 20 chars max
2014-07-30 | A Home Page | 1 | 9 | Standards | Returned time doesn’t match | Rudhra | Rudhra | 2014-08-16 | FIXED
2014-07-30 | I Polling | 2 | 10 | Functionality | Processing takes longer time to store the data’s into database. | Rudhra |  |  | PENDING
2014-07-30 | I Polling | 3 | 10 | Functionality | Edit polling form is not displaying its relevant data’s from database | Rudhra | Rudhra |  | FIXED
2014-07-30 | H Sponsors | 1 | 5 | Standards | Date stamp should be directly below the table | Rudhra | Rudhra | 2014-08-16 | FIXED
2014-07-30 | H Sponsors | 1 | 8 | Standards | Date stamp should match the system time | Rudhra | Rudhra | 2014-08-16 | FIXED
2014-07-30 | H Sponsors | 2 | 3 | Functionality | Add sponsor page is not properly displayed in chrome browser. | Rudhra |  |  | PENDING
2014-07-30 | H Sponsors | 2 | 8 | Functionality | Duplicate entry should not be added | Rudhra |  |  | ? | allow to sponsor multiple items
2014-07-30 | H Sponsors | 2 | 9 | Functionality | Website address is not properly validated. | Rudhra | Rudhra | 2014-08-27 | FIXED
2014-07-30 | H Sponsors | 2 | 11,12 | Functionality | image or file path is not stored in the database. | Rudhra |  |  | ?
2014-07-30 | H Sponsors | 2 | 14 | Functionality | Reset button must be able to clear any warnings displayed | Rudhra | Rudhra | 2014-08-26 | FIXED
2014-07-30 | H Sponsors | 3 | 2 | Functionality | Edit sponsor page doesn’t provide any option to edit the logo or image. | Rudhra |  |  | PENDING
2014-07-30 | H Sponsors | 3 | 5 | Functionality | Reset button must be able to clear any warnings displayed | Rudhra | Rudhra | 2014-08-26 | FIXED
2014-07-30 | H Sponsors | 3 | 8 | Functionality | Website address is not properly validated. | Rudhra | Rudhra | 2014-08-27 | FIXED
2014-08-01 | B Login | 1 | 8 | Functionality | There is no warning message for invalid email id in reset password. | Rudhra | Rudhra | 2014-08-26 | FIXED
2014-08-01 | B Login | 1 | 9 | Functionality | No successful message for entering valid email id in reset password options. | Rudhra | Rudhra | 2014-08-26 | FIXED
2014-08-01 | B Login |  | 10 | Functionality | No validation for email id matching to the database in reset password. | Rudhra | Rudhra | 2014-08-26 | FIXED
2014-08-30 | U Venues | 1 | 5,8 | Standards | Datestamp is missing | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-30 | U Venues | 2 | 3 | Standards | No reset button | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-30 | U Venues | 2 | 7 | Functionality | Postcode validation failed | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-30 | U Venues | 2 | 9 | Functionality | completed and valid fields should not be cleared when the other fields are incomplete during submission. | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-30 | U Venues | 3 | 2,5,10 | Standards | No reset button | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-30 | U Venues | 3 | 11 | Standards | No datetime shown | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-30 | U Venues | 4 | 2 | Standards | "Go Back" Button is missing | Rudhra | Shuhei | 2014-08-30 | PENDING
2014-08-01 | G Add Presenter | 2 | 11 | Functionality | When add a presenter it does not return a confirmation to user | Paulo | Rudhra |  | FIXED | Works fine
2014-08-01 | G Edit Presenter | 3 | 3 | Standards | Not button to add or edit current file | Paulo | Rudhra |  | FIXED
2014-08-01 | Q Add user | 3 | 5 | Standards | Password should be hidden when typing | Paulo | Rudhra | 2014-08-15 | FIXED
2014-08-01 | Q Add user | 3 | 10 | Standards | It should allow user to input blank space in a few fields | Paulo | Rudhra |  | FIXED
2014-08-01 | Q Delete user | 4 | 4 | Standards | Password is displayed, big vulnerability | Paulo | Rudhra | 2014-08-15 | FIXED
2014-08-01 | C Navigation | 1 | 7 | Functionality | When you are editing, or adding something and want's to go back to list by clicking on navigation, it doesnt | Paulo | Rudhra |  | FIXED | Works fine
2014-08-01 | D Section | 1 | 1 | Functionality | Conference linked to section is not displayed | Jack | Rudhra | 2014-08-24 | FIXED
2014-08-01 | D Section | 2 | 4 | Functionality | No error message after submitting invalid data | Jack | Rudhra | 2014-08-26 | FIXED
2014-08-01 | E Conference | 1 | 4 | Functionality | Conferences not sorted alphabetically | Jack | Rudhra | 2014-08-26 | FIXED
2014-08-01 | E Conference | 2 | 1 | Functionality | No way to edit conference image | Jack |  |  | PENDING
2014-08-01 | F Session | 2 | 3 | Functionality | Adding a session with an end date before the start date does not result in an error | Jack | Rudhra | 2014-08-20 | FIXED
2014-08-01 | FeedBack |  |  | Functionality | Delete Question Doesn't work in the feedback section | Shuhei | Rudhra | 2014-08-27 | FIXED

## Fault_Summary Con04
Fault Summary
Date | Test No | Error | Issued to | Date Retested | OK?
2014-06-06 | H1 Sponsor | STANDARDS: Time is displayed above "Add" Button |  |  | PENDING
2014-06-06 | H1 Sponsor | FUNCTIONALITY: Larger File Size, Validation of address |  |  | PENDING | Caue
2014-06-06 | H1 Sponsor | FUNCTIONALITY: Reset button does not reset |  |  | PENDING | Shohei
2014-06-06 | H1 Sponsor | FUNCTIONALITY: IE & Firefox drop down boxes require double clicks |  |  | PENDING | Tom
2014-06-06 | H1 Sponsor | FUNCTIONALITY: Edit Sponsor Logo, logo cannot be changed. |  |  | PENDING | Will
Jenny
2014-06-05 | G1 Presenters | STANDARDS: All html attributes use single quotation marks |  |  | PENDING
2014-06-05 | G1 Presenters | FUNCTIONALITY: Filepath is always the same as 'File Uploaded'. |  |  | PENDING
2014-06-05 | G3 Presenters | INTERFACE: Edit Page missing field for file path. |  |  | PENDING
2014-06-05 | I1 Polling | STANDARDS: Curly Bracket 'Java Style' Not followed. |  |  | PENDING
2014-06-05 | I2 Polling | INTERFACE: Add page missing 2 drop downs boxes for Conference and Section. |  |  | PENDING
2014-06-05 | I3 Polling | STANDARDS: All html attributes use single quotation marks |  |  | PENDING
2014-06-05 | J1 Polling Results | STANDARDS: Curly Bracket 'Java Style' Not followed. |  |  | PENDING
2014-06-05 | J2 Polling Results | FUNCTIONALITY: Option of Zero Vote, resultant should not be displayed |  |  | PENDING
2014-06-05 | J3 Polling Results | FUNCTIONALITY: Option of Zero Vote, resultant should not be displayed |  |  | PENDING
05/0605/06/2014 | K1 Feedback Forms | FUNCTIONALITY: No validation for special characters. |  |  | PENDING
05/0605/06/2014 | L Feedback Questions | FUNCTIONALITY: Drop down list differ from database. |  |  | PENDING
05/0605/06/2014 | L Feedback Questions | FUNCTIONALITY: Special Characters causing information problems. Eg commas |  |  | PENDING
05/0605/06/2014 | L Feedback Questions | FUNCTIONALITY: Deleting a feed question causes web server crash |  |  | PENDING
05/0605/06/2014 | Q Users | FUNCTIONALITY: Special Characters causing information problems. Eg commas |  |  | PENDING
05/0605/06/2014 | Q Users | REQUIREMENT: Password not shown in edit and deletion tables. |  |  | PENDING
2014-06-05 | F2 Sessions | REQUIREMENT: Page drop down list should be populated by conferences |  |  | PENDING
2014-06-04 | C1 Navigation Bar | FUNCTIONALITY: No inline comments, no function header comment |  |  | PENDING
2014-06-04 | C1 Navigation Bar | STANDARDS: No page loading from Sponsors. |  |  | PENDING
2014-06-04 | C1 Navigation Bar | STANDARDS: No page showing after Add selected by Quesions, Sponsors and Maps. |  |  | PENDING
LIVE FAULT REPORT
2014-06-09 | D2 Conference Section | FUNCTIONALITY:Non Number entered into 'Section Order', the system doesn't save information |  |  | PENDING
2014-06-09 | D2 Conference Section | FUNCTIONALITY: Special Characters causing information issues. |  |  | PENDING
2014-06-09 | E2 Conference | FUNCTIONALITY: Delete confirmation page column "Venue" left open. |  |  | PENDING
2014-06-09 | J2 Polling Result | FUNCTIONALITY: Missing Logo, Filename,Description, Author and Last Update |  |  | PENDING
2014-06-09 | Q1 Users | FUNCTIONALITY: Password Check Problems, password not checked verse each other. |  |  | PENDING

## Test_Summary Con04
Test Summary - Initial Testing
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested | Ok?
H | H1.1 | White Box Static | Integration | Sponsors | Chrome, IE and Firefox | Caue | 2014-06-11 | Ok
| H1.2 | White Box Dynamic | Integration | Sponsors | Chrome, IE and Firefox | Caue | 2014-06-11 | FAIL
| H1.3 | Black Box | Integration | Sponsors | Chrome, IE and Firefox | Caue | 2014-06-11 | Ok
M | M1.1 | Whitebox Static | Integration | Q and A | Chrome, IE and Firefox | Caue | 2014-06-11 | Ok
| M2.1 | Whitebox Dynamic | Integration | Q and A | Chrome, IE and Firefox | Caue | 2014-06-11 | Ok
| M3.1 | Blackbox | Integration | Q and A | Chrome, IE and Firefox | Caue | 2014-06-11 | Ok
O | O1.1 | Whitebox Static | Integration | Maps | Chrome, IE and Firefox | Caue | 2014-05-22 | Ok
| O1.2 | Whitebox Dynamic | Integration | Maps | Chrome, IE and Firefox | Caue | 2014-05-22 | FAIL
| O1.3 | Blackbox | Integration | Maps | Chrome, IE and Firefox | Caue | 2014-05-22 | Ok
A | X1.1 | Whitebox Static | Integration | Home Page | Chrome, IE and Firefox | Jenny | 2014-06-04 | Ok
| X2.1 | Whitebox Dynamic | Integration | Home Page | Chrome, IE and Firefox | Jenny | 2014-06-04 | Ok
| X3.1 | Blackbox | Integration | Home Page | Chrome, IE and Firefox | Jenny | 2014-06-04 | Ok
C | C1.1 | Whitebox Static | Integration | Navigation Bar | Chrome, IE and Firefox | Jenny | 2014-06-04 | FAIL
| C2.1 | Whitebox Dynamic | Integration | Navigation Bar | Chrome, IE and Firefox | Jenny | 2014-06-04 | FAIL
| C3.1 | Whitebox Dynamic | Integration | Navigation Bar | Chrome, IE and Firefox | Jenny | 2014-06-04 | FAIL
E | E1.1 | Whitebox Static | Integration | Conference | Chrome, IE and Firefox | Jenny | 2014-06-04 | Ok
| E2.1 | Whitebox Dynamic | Integration | Conference | Chrome, IE and Firefox | Jenny | 2014-06-04 | Ok
| E3.1 | Blackbox | Integration | Conference | Chrome, IE and Firefox | Jenny | 2014-06-04 | Ok
G | G1.1 | Whitebox Static | Integration | Presenters | Chrome, IE and Firefox | Shohei | 2014-06-04 | Ok
| G2.1 | Whitebox Dynamic | Integration | Presenters | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
| G3.1 | Blackbox | Integration | Presenters | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
I | I1.1 | Whitebox Static | Integration | Polling | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
| I2.1 | Whitebox Dynamic | Integration | Polling | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
| I3.1 | Blackbox | Integration | Polling | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
J | J1.1 | Whitebox Static | Integration | Polling Results | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
| J2.1 | Whitebox Dynamic | Integration | Polling Results | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
| J3.1 | Blackbox | Integration | Polling Results | Chrome, IE and Firefox | Shohei | 2014-06-04 | FAIL
K | K1.1 | Whitebox Static | Integration | Feedback Reports | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
| K2.1 | Whitebox Dynamic | Integration | Feedback Reports | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
| K3.1 | Blackbox | Integration | Feedback Reports | Chrome, IE and Firefox | Tom | 2014-06-05 | Ok
L | L1.1 | Whitebox Static | Integration | Feedback Questions | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
| L2.1 | Whitebox Dynamic | Integration | Feedback Questions | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
| L3.1 | Blackbox | Integration | Feedback Questions | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
Q | Q1.1 | Whitebox Static | Integration | Users | Chrome, IE and Firefox | Tom | 2014-06-05 | Ok
| Q2.1 | Whitebox Dynamic | Integration | Users | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
| Q3.1 | Blackbox | Integration | Users | Chrome, IE and Firefox | Tom | 2014-06-05 | FAIL
B | B1.1 | Whitebox Static | Integration | Login Security | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
| B2.1 | Whitebox Dynamic | Integration | Login Security | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
| B3.1 | Blackbox | Integration | Login Security | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
D | D1.1 | Whitebox Static | Integration | Conference Section | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
| D2.1 | Whitebox Dynamic | Integration | Conference Section | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
| D3.1 | Blackbox | Integration | Conference Section | Chrome, IE and Firefox | Will | 2014-06-05 | FAIL
F | F1.1 | Whitebox Static | Integration | Session | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
| F2.1 | Whitebox Dynamic | Integration | Session | Chrome, IE and Firefox | Will | 2014-06-05 | FAIL
| F3.1 | Blackbox | Integration | Session | Chrome, IE and Firefox | Will | 2014-06-05 | Ok
LIVE TESTING
D | D1.1 | Whitebox Static | Integration | Conference Section | Chrome, IE and Firefox | Shohei | 2014-06-09 | FAIL
| D2.1 | Whitebox Dynamic | Integration | Conference Section | Chrome, IE and Firefox | Shohei | 2014-06-09 | FAIL
| D3.1 | Blackbox | Integration | Conference Section | Chrome, IE and Firefox | Shohei | 2014-06-09 | FAIL
E | E1.1 | Whitebox Static | Integration | Conference | Chrome, IE and Firefox | Shohei | 2014-06-09 | Ok
| E2.1 | Whitebox Dynamic | Integration | Conference | Chrome, IE and Firefox | Shohei | 2014-06-09 | Ok
| E3.1 | Blackbox | Integration | Conference | Chrome, IE and Firefox | Shohei | 2014-06-09 | FAIL
J | J1.1 | Whitebox Static | Integration | Polling Result | Chrome, IE and Firefox | Shohei | 2014-06-05 | FAIL
| J2.1 | Whitebox Dynamic | Integration | Polling Result | Chrome, IE and Firefox | Shohei | 2014-06-05 | Ok
| J3.1 | Blackbox | Integration | Polling Result | Chrome, IE and Firefox | Shohei | 2014-06-05 | Ok
Q | Q1.1 | Whitebox Static | Integration | Users | Chrome, IE and Firefox | Shohei | 2014-06-05 | FAIL
| Q2.1 | Whitebox Dynamic | Integration | Users | Chrome, IE and Firefox | Shohei | 2014-06-05 | FAIL
| Q3.1 | Blackbox | Integration | Users | Chrome, IE and Firefox | Shohei | 2014-06-05 | FAIL

## Fault_Summary Con03
Fault Summary
Date | Test No | Error | Issued to | Date Retested | OK?
2014-05-18 | S1.1 Add Presenter | Name of picture does not change to ID | Jenny | NEXT ITERATION | PENDING
2014-05-18 | E2.1 Add Conference | Name of picture does not change to ID | Jenny | NEXT ITERATION | PENDING | Jenny
2014-05-18 | H1.1 Add Sponsor | Name of picture does not change to ID | Jenny | NEXT ITERATION | PENDING | Will
2014-05-22 | M3.1 Q_A | Incorrect table and field being queried. | Will | NEXT ITERATION | PENDING

## Test_Summary Con03
Test Summary - Initial Testing
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested | Ok?
C | C1.1 | White Box Static | Integration | Navigation Bar | Chrome, IE and Firefox | Caue Shohei | 2014-05-21 | Ok
| C3.1 | Black Box | Integration | Navigation Bar | Chrome, IE and Firefox | Caue Shohei | 2014-05-21 | Ok
I | I1 | Whitebox Static | Integration | Manage Polling Availability | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| I2 | Whitebox Dynamic | Integration | Manage Polling Availability | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| I3 | Blackbox | Integration | Manage Polling Availability | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
O | O1.1 | Whitebox Static | Integration | Manage Polling Availability | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| O1.2 | Whitebox Dynamic | Integration | Manage Polling Availability | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| O1.3 | Blackbox | Integration | Manage Polling Availability | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
X | X1.1 | Whitebox Static | Integration | Assign presenters to a session | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| X1.2 | Whitebox Static | Integration | Assign presenters to a session | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| X2.1 | Whitebox Dynamic | Integration | Assign presenters to a session | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| X2.2 | Whitebox Dynamic | Integration | Assign presenters to a session | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| X3.1 | Blackbox | Integration | Assign presenters to a session | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
| X3.2 | Blackbox | Integration | Assign presenters to a session | Chrome, IE and Firefox | Shohei | 2014-05-22 | Ok
S | S1.1U | Whitebox Static | Unit | File upload in Validation | Chrome, IE and Firefox | Jenny | 2014-05-18 | Ok
| S1.2U | Whitebox Static | Unit | File upload in Add (Presenters) | Chrome, IE and Firefox | Jenny | 2014-05-18 | Ok
| S1.3U | Whitebox Static | Unit | File upload in Edit (Presenters) | Chrome, IE and Firefox | Jenny | 2014-05-18 | Ok
| S2.1 | Whitebox Dynamic | Integration | File upload (Presenters) | Chrome, IE and Firefox | Jenny | 2014-05-18 | Ok
| S2.2 | Whitebox Dynamic | Integration | File upload in Add (Presenters) | Chrome, IE and Firefox | Jenny | 2014-05-18 | FAIL
| S2.3 | Whitebox Dynamic | Integration | File upload in Add Conference | Chrome, IE and Firefox | Jenny | 2014-05-18 | FAIL
| S2.4 | Whitebox Dynamic | Integration | File upload in Add Conference | Chrome, IE and Firefox | Jenny | 2014-05-18 | FAIL
H | H1.1 | Whitebox Static | Integration | Add Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H1.2 | Whitebox Static | Integration | Edit Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H1.3 | Whitebox Static | Integration | Delete Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H2.1 | Whitebox Dynamic | Integration | View Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H2.2 | Whitebox Dynamic | Integration | Add Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H2.3 | Whitebox Dynamic | Integration | Edit Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H2.4 | Whitebox Dynamic | Integration | Delete Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H3.1 | Blackbox | Integration | View Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H3.2 | Blackbox | Integration | Add Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H3.3 | Blackbox | Integration | Edit Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
| H3.4 | Blackbox | Integration | Delete Sponsors | Chrome, IE and Firefox | Tom | 2014-05-21 | Ok
M | M1.1 | Whitebox Static | Integration | Review Questions | Chrome, IE and Firefox | Will | 2014-05-22 | Ok
| M1.2 | Whitebox Static | Integration | RSS | Chrome, IE and Firefox | Will | 2014-05-22 | Ok
| M2.1 | Whitebox Dynamic | Integration | Review Questions | Chrome, IE and Firefox | Will | 2014-05-22 | Ok
| M2.2 | Whitebox Dynamic | Integration | RSS | Chrome, IE and Firefox | Will | 2014-05-22 | Ok
| M3.1 | Blackbox | Integration | Review Questions | Chrome, IE and Firefox | Will | 2014-05-22 | FAIL
| M3.2 | Blackbox | Integration | RSS | Chrome, IE and Firefox | Will | 2014-05-22 | Ok
Test Scripts
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested | Ok?
C | C1.1 | Whitebox Static | Integration | Navigation Bar | Chrome, IE and Firefox | Shohei | 2014-04-22 | Ok
| C3.1 | Blackbox | Integration | Navigation Bar | Chrome, IE and Firefox | Shohei | 2014-04-22 | Ok
H | H3.1 | Blackbox | Integration | View Sponsor | Chrome, IE and Firefox | Jenny | 2014-05-23 | Ok
| H3.2 | Blackbox | Integration | Add Sponsor | Chrome, IE and Firefox | Jenny | 2014-05-23 | Ok
| H3.3 | Blackbox | Integration | Edit Sponsor | Chrome, IE and Firefox | Jenny | 2014-05-23 | Ok
| H3.4 | Blackbox | Integration | Delete Sponsor | Chrome, IE and Firefox | Jenny | 2014-05-23 | Ok

## Test_Summary Con01
Test Summary - Initial Testing
Annex | Test No | Test Type | Test Level | Program Name | Browser | Assigned to | Date Tested | Date retested | Ok?
B
B3 | B3-1 | Blackbox | Integration | Check User ID and password and allow access when correct.
| B3-2 | Blackbox | Integration | Conference Administrators gain access to their Conference Data.
| B3-3 | Blackbox | Integration | Test connection to database, report error if connectivity problem.
| B3-4 | Blackbox | Integration | Submit login information to database report if login details incorrect.
| B3-5 | Blackbox | Integration | All Web pages must check that the user is logged on and authenticated
D | D1.1 | Blackbox | Integration | View Section | Chrome | Jenny Jen | 2014-03-20 |  | OK
| D1.2 | Blackbox | Integration | View Section | Firefox | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D1.3 | Blackbox | Integration | View Section | Internet Explorer | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D2.1 | Blackbox | Integration | Add Conference Section | Chrome | Jenny Jen | 2014-03-20 |  | OK
| D2.2 | Blackbox | Integration | Add Conference Section | Firefox | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D2.3 | Blackbox | Integration | Add Conference Section | Internet Explorer | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D3.1 | Blackbox | Integration | Delete Conference Section | Chrome | Jenny Jen | 2014-03-20 |  | OK
| D3.2 | Blackbox | Integration | Delete Conference Section | Firefox | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D3.3 | Blackbox | Integration | Delete Conference Section | Internet Explorer | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D4.1 | Blackbox | Integration | Edit Conference Section | Chrome | Jenny Jen | 2014-03-20 |  | OK
| D4.2 | Blackbox | Integration | Edit Conference Section | Firefox | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D4.3 | Blackbox | Integration | Edit Conference Section | Internet Explorer | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
E | E1.1 | Blackbox | Integration | View Conference | Chrome | Andy | 2014-03-20 |  | OK
| E1.2 | Blackbox | Integration | View Conference | Firefox | Andy | 2014-03-20 |  | OK
| E1.3 | Blackbox | Integration | View Conference | Internet Explorer | Andy | 2014-03-20 |  | OK
| E2.1 | Blackbox | Integration | Add Conference | Chrome | Andy | 2014-03-20 |  | OK
| E2.2 | Blackbox | Integration | Add Conference | Firefox | Andy | 2014-03-20 |  | OK
| E2.3 | Blackbox | Integration | Add Conference | Internet Explorer | Andy | 2014-03-20 |  | OK
| E3.1 | Blackbox | Integration | Delete Conference | Chrome | Andy | 2014-03-20 |  | OK
| E3.2 | Blackbox | Integration | Delete Conference | Firefox | Andy | 2014-03-20 |  | OK
| E3.3 | Blackbox | Integration | Delete Conference | Internet Explorer | Andy | 2014-03-20 |  | OK
| E4.1 | Blackbox | Integration | Edit Conference | Chrome | Andy | 2014-03-20 |  | OK
| E4.2 | Blackbox | Integration | Edit Conference | Firefox | Andy | 2014-03-20 |  | OK
| E4.3 | Blackbox | Integration | Edit Conference | Internet Explorer | Andy | 2014-03-20 |  | OK
| ERW01 | Whitebox | Unit | View Conference | N/a | Andy | 2014-03-21 | 2013-03-21 | OK
| ERW02 | Whitebox | Unit | Add Conference | N/a | Andy | 2014-03-21 | 2013-03-21 | OK
| ERW03 | Whitebox | Unit | Delete Conference | N/a | Andy | 2014-03-21 |  | OK
| ERW04 | Whitebox | Unit | Edit Conference | N/a | Andy | 2014-03-21 |  | OK
F | F1.1 | Blackbox | Integration | View Session | Chrome | Tom | 2014-03-17 |  | OK
| F1.2 | Blackbox | Integration | View Session | Firefox | Tom | 2014-03-17 |  | OK
| F1.3 | Blackbox | Integration | View Session | Internet Explorer | Tom | 2014-03-17 |  | OK
| F2.1 | Blackbox | Integration | Add Session | Chrome | Tom | 2014-03-17 |  | OK
| F2.2 | Blackbox | Integration | Add Session | Firefox | Tom | 2014-03-17 |  | OK
| F2.3 | Blackbox | Integration | Add Session | Internet Explorer | Tom | 2014-03-17 |  | OK
| F3.1 | Blackbox | Integration | Delete Session | Chrome | Tom | 2014-03-17 |  | OK
| F3.2 | Blackbox | Integration | Delete Session | Firefox | Tom | 2014-03-17 |  | OK
| F3.3 | Blackbox | Integration | Delete Session | Internet Explorer | Tom | 2014-03-17 |  | OK
| F4.1 | Blackbox | Integration | Edit Session | Chrome | Tom | 2014-03-17 |  | OK
| F4.2 | Blackbox | Integration | Edit Session | Firefox | Tom | 2014-03-17 |  | OK
| F4.3 | Blackbox | Integration | Edit Session | Internet Explorer | Tom | 2014-03-17 |  | OK
| FRW01 | Whitebox | Unit | View Session | N/a | Tom | 2014-03-21 |  | OK
| FRW02 | Whitebox | Unit | Add Session | N/a | Tom | 2014-03-21 |  | OK
| FRW03 | Whitebox | Unit | Delete Session | N/a | Tom | 2014-03-21 |  | OK
| FRW04 | Whitebox | Unit | Edit Session | N/a | Tom | 2014-03-21 |  | OK
G | G1.1 | Blackbox | Integration | View Presenter | Chrome | Will | 2014-03-20 |  | OK
| G1.2 | Blackbox | Integration | View Presenter | Firefox | Will | 2014-03-20 |  | OK
| G1.3 | Blackbox | Integration | View Presenter | Internet Explorer | Will | 2014-03-20 |  | OK
| G2.1 | Blackbox | Integration | Add Presenter | Chrome | Will | 2014-03-20 |  | OK
| G2.2 | Blackbox | Integration | Add Presenter | Firefox | Will | 2014-03-20 |  | OK
| G2.3 | Blackbox | Integration | Add Presenter | Internet Explorer | Will | 2014-03-20 |  | OK
| G3.1 | Blackbox | Integration | Delete Presenter | Chrome
| G3.2 | Blackbox | Integration | Delete Presenter | Firefox
| G3.3 | Blackbox | Integration | Delete Presenter | Internet Explorer
| G4.1 | Blackbox | Integration | Edit Presenter | Chrome
| G4.2 | Blackbox | Integration | Edit Presenter | Firefox
| G4.3 | Blackbox | Integration | Edit Presenter | Internet Explorer
| GRW01 | Whitebox | Unit | View Presenter | N/a | Will | 2014-03-21 |  | OK
| GRW02 | Whitebox | Unit | Add Presenter | N/a | Will | 2014-03-21 |  | OK
H | H1.1 | Blackbox | Integration | View Sponsor | Chrome
| H1.2 | Blackbox | Integration | View Sponsor | Firefox
| H1.3 | Blackbox | Integration | View Sponsor | Internet Explorer
| H2.1 | Blackbox | Integration | Add Sponsor | Chrome
| H2.2 | Blackbox | Integration | Add Sponsor | Firefox
| H2.3 | Blackbox | Integration | Add Sponsor | Internet Explorer
| H3.1 | Blackbox | Integration | Delete Sponsor | Chrome
| H3.2 | Blackbox | Integration | Delete Sponsor | Firefox
| H3.3 | Blackbox | Integration | Delete Sponsor | Internet Explorer
| H4.1 | Blackbox | Integration | Edit Sponsor | Chrome
| H4.2 | Blackbox | Integration | Edit Sponsor | Firefox
| H4.3 | Blackbox | Integration | Edit Sponsor | Internet Explorer
| H5.1 | Blackbox | Integration | Update Sponsor | Chrome
| H5.2 | Blackbox | Integration | Update Sponsor | Firefox
| H5.3 | Blackbox | Integration | Update Sponsor | Internet Explorer
I | I1.1 | Blackbox | Integration | Manage Maps | Chrome
| I1.2 | Blackbox | Integration | Manage Maps | Firefox
| I1.3 | Blackbox | Integration | Manage Maps | Internet Explorer
S | S1.1 | Blackbox | Integration | Access Help | Chrome
| S1.2 | Blackbox | Integration | Access Help | Firefox
| S1.3 | Blackbox | Integration | Access Help | Internet Explorer
T | T1.1 | Blackbox | Integration | Initial Download | Chrome
| T1.2 | Blackbox | Integration | Initial Download | Firefox
| T1.3 | Blackbox | Integration | Initial Download | Internet Explorer

## Regression_Testing Con01
Test Summary - Regression Testing
Annex | Test No | Test Type | Test Level | Program Name | Browser | Assigned to | Date Tested | Date retested | Ok?
D | D4.2 | Blackbox | Integration | Edit Conference Section | Firefox | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
| D4.3 | Blackbox | Integration | Edit Conference Section | Internet Explorer | Jenny Jen | 2014-03-20 | 2014-03-21 | OK
E | ERW01 | Whitebox | Unit | View Conference | N/a | Andy | 2014-03-21 | 2013-03-21 | OK
| ERW02 | Whitebox | Unit | Add Conference | N/a | Andy | 2014-03-21 | 2013-03-21 | OK
F | FRW01 | Whitebox | Unit | View Conference | N/a | Tom | 2014-03-21 |  | OK
| FRW02 | Whitebox | Unit | Add Conference | N/a | Tom | 2014-03-21 |  | OK
| FRW03 | Whitebox | Unit | Delete Conference | N/a | Tom | 2014-03-21 |  | OK
| FRW04 | Whitebox | Unit | Edit Conference | N/a | Tom | 2014-03-21 |  | OK
G

## Fault_Summary Con01
Fault Summary
Date | Test No | Error | Issued to | Date Retested | OK?
2014-03-21 | ERW01 | Missing File Comments (Team logo, Date, Used by | Andy | 2014-03-21 | OK
2014-03-21 | ERW02 | Missing File Comments (Team logo, Date, Used by | Andy | 2014-03-21 | OK
2014-03-21 | Annex E - User Acceptance Conference Chrome | Missing in Edit Conference Title | Jenny | 2014-03-21 | OK
2014-03-21 | Annex E - User Acceptance Conference IE | Missing in Edit Conference Title | Jenny | 2014-03-21 | OK

## Test_Summary Con02
Test Summary - Initial Testing
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested |  | Ok?
I | I1.1 | Whitebox Static | Integration | View Polling | Chrome, IE and Firefox | Caue | 2014-04-25 | Will | Ok
| I1.2 | Whitebox Static | Integration | Add Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
| I1.3 | Whitebox Static | Integration | Delete Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
| I1.4 | Whitebox Static | Integration | Edit Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
| I3.1 | Black Box | Integration | View Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
| I3.2 | Black Box | Integration | Add Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
| I3.3 | Black Box | Integration | Delete Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
| I3.4 | Black Box | Integration | Edit Polling | Chrome, IE and Firefox | Caue | 2014-04-25 |  | Ok
J | J1.1 | Whitebox Static | Integration | Present a system to navigate to the desired session | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| J1.2 | Whitebox Static | Integration | List the question and a graph of polling results. (and move to next question if required) | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| J3.1 | Black Box | Integration | Present a system to navigate to the desired session | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| J3.2 | Black Box | Integration | List the question and a graph of polling results. (and move to next question if required) | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
K | K1.3 | Whitebox Static | Integration | Edit an existing feedback form together with its sections | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| K3.1 | Black Box | Integration | Display all conferences in a table format -> Select feedback link. Display Conference Feedback form including its sections (many of these) | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| K3.2 | Black Box | Integration | Create a new feedback form together with its sections | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| K3.3 | Black Box | Integration | Edit an existing feedback form together with its sections | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| K3.4 | Black Box | Integration | Delete an existing feedback form together with its sections (after confirmation) | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| K3.5 | Black Box | Integration | Display updated Conference feedback for after changes are complete | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
L | L1.3 | Whitebox Static | Integration | Edit Feedback Question | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
| L3.1 | Black Box | Integration | Edit Feedback Question | Chrome, IE and Firefox | Shohei | 2014-04-26 |  | Ok
G | G1.1 | Whitebox Static | Integration | Delete a Presenter and his/her bio details including a photo | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | Ok
| G1.2 | Whitebox Static | Integration | Display a refreshed view of all presenters after any changes are complete | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | Ok
| G1.3 | Whitebox Static | Integration | Edit Presenter and his/her bio | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | Ok
| G2.1 | Whitebox Dynamic | Integration | Edit Presenter and his/her bio | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | FAIL
| G2.2 | Whitebox Dynamic | Integration | Delete a Presenter and his/her bio details including a photo | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | Ok
| G3.1 | Black Box | Integration | Edit Presenter and his/her bio | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | FAIL
| G3.2 | Black Box | Integration | Delete a Presenter and his/her bio details including a photo | Chrome, IE and Firefox | Jenny Jen | 2014-04-23 |  | Ok
Q | Q1.1 | Whitebox Static | Integration | Present Users | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q1.2 | Whitebox Static | Integration | Add Users | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q1.3 | Whitebox Static | Integration | Delete Users | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q1.4 | Whitebox Static | Integration | Edit Users | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q2.1 | Whitebox Dynamic | Integration | View Users | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q2.2 | Whitebox Dynamic | Integration | Edit User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q2.3 | Whitebox Dynamic | Integration | Add User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | FAIL
| Q2.4 | Whitebox Dynamic | Integration | Delete User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q3.1 | Black Box | Integration | View Users | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q3.2 | Black Box | Integration | Edit User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
| Q3.3 | Black Box | Integration | Add User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | FAIL
| Q3.4 | Black Box | Integration | Delete User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24 |  | Ok
U | U1.1 | Whitebox Static | Integration | Download all data for that conference, including sessions presenters, Feedback Questions. (Activated on the first use of the conference code). | Chrome, IE and Firefox | Tom | 2014-04-24 |  | Ok
| U1.2 | Whitebox Static | Integration | Check for latest version of the data. If changes have been made, provide update to mobile app. | Chrome, IE and Firefox | Tom | 2014-04-24 |  | Ok
| U2.1 | Whitebox Dynamic | Integration | Download all data for that conference, including sessions presenters, Feedback Questions. (Activated on the first use of the conference code). | Chrome, IE and Firefox | Tom | 2014-04-24 |  | Ok
| U2.2 | Whitebox Dynamic | Integration | Check for latest version of the data. If changes have been made, provide update to mobile app. | Chrome, IE and Firefox | Tom | 2014-04-24 |  | Ok
| U3.1 | Black Box | Integration | Download all data for that conference, including sessions presenters, Feedback Questions. (Activated on the first use of the conference code). | Chrome, IE and Firefox | Tom | 2014-04-24 |  | Ok
| U3.2 | Black Box | Integration | Check for latest version of the data. If changes have been made, provide update to mobile app. | Chrome, IE and Firefox | Tom | 2014-04-24 |  | Ok
V | V1.1 | Whitebox Static | Integration | Accept Polling data | Chrome, IE and Firefox | Tom | 2014-04-25 |  | Ok
| V1.2 | Whitebox Static | Integration | Accept Attendee Profile | Chrome, IE and Firefox | Tom | 2014-04-25 |  | Ok
| V2.1 | Whitebox Dynamic | Integration | Accept Polling data | Chrome, IE and Firefox | Tom | 2014-04-26 |  | Ok
| V2.2 | Whitebox Dynamic | Integration | Accept Attendee Profile | Chrome, IE and Firefox | Tom | 2014-04-26 |  | Ok
| V3.1 | Black Box | Integration | Accept Polling data | Chrome, IE and Firefox | Tom | 2014-04-26 |  | Ok
| V3.2 | Black Box | Integration | Accept Attendee Profile | Chrome, IE and Firefox | Tom | 2014-04-26 |  | Ok
W | W1.1 | Whitebox Static | Integration | Index.php (webservice) | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
| W3.1 | Black Box | Integration | Index.php (webservice) | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
X | X1.1 | Whitebox Static | Integration | Index.php (webservice) | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
| X3.1 | Black Box | Integration | Index.php (webservice) | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
Test Scripts
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested |  | Ok?
B | B1.1 | Whitebox Static | Integration | Login / Security | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
| B3.1 | Blackbox | Integration | Login / Security | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
E | E1.1 | Whitebox Static | Integration | cloneView.php | Chrome, IE and Firefox | Will | 2014-04-26 |  | Ok
| E1.2 | Whitebox Static | Integration | clone.php | Chrome, IE and Firefox | Will | 2014-04-27 |  | Ok
| E3.1 | Blackbox | Integration | Clone a Conference | Chrome, IE and Firefox | Will | 2014-04-26 |  | FAIL
G | G1 | Blackbox | Integration | View Presenter | Chrome, IE and Firefox | Tom | 2014-04-27 |  | Ok
| G2 | Blackbox | Integration | Delete Presenter | Chrome, IE and Firefox | Tom | 2014-04-27 |  | Ok
| G3 | Blackbox | Integration | Edit Presenter | Chrome, IE and Firefox | Tom | 2014-04-27 |  | FAIL
Q | Q1 | Blackbox | Integration | View Users | Chrome, IE and Firefox | Tom | 2014-04-26 |  | Ok
| Q2 | Blackbox | Integration | Edit User | Chrome, IE and Firefox | Tom | 2014-04-26 |  | FAIL
| Q3 | Blackbox | Integration | Add User | Chrome, IE and Firefox | Tom | 2014-04-26 |  | FAIL
| Q4 | Blackbox | Integration | Delete User | Chrome, IE and Firefox | Tom | 2014-04-26 |  | Ok
U | U1.1 | Blackbox | Integration | Download all data for that conference, including sessions presenters, Feedback Questions etc (Activated on first use of the conference code) | Chrome, IE and Firefox | Jenny | 2014-04-26 |  | Ok
| U1.2 | Blackbox | Integration | Check for latest version of the data. If changes have been made, provide update to mobile app. | Chrome, IE and Firefox | Jenny | 2014-04-26 |  | Ok
V | V1.1 | Blackbox | Integration | Accept Polling Data | Chrome, IE and Firefox | Jenny | 2014-04-26 |  | Ok
| V1.2 | Blackbox | Integration | Accept Attendee Profile | Chrome, IE and Firefox | Jenny | 2014-04-26 |  | Ok

## Regression_Testing Con02
Will
Test Summary - Initial Testing
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested | Re Test | Ok?
G | G2.1 | Whitebox Dynamic | Integration | Edit Presenter and his/her bio | Chrome, IE and Firefox | Jenny Jen | 2014-04-23
| G3.1 | Black Box | Integration | Edit Presenter and his/her bio | Chrome, IE and Firefox | Jenny Jen | 2014-04-23
Q | Q2.3 | Whitebox Dynamic | Integration | Add User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24
| Q3.3 | Black Box | Integration | Add User | Chrome, IE and Firefox | Jenny Jen | 2014-04-24
Test Scripts - REGRESSION
Annex | Test No | Test Type | Test Level | Program Name | Browsers | Assigned to | Date Tested | Re Test | Ok?
G | G3 | Blackbox | Integration | Edit Presenter | Chrome, IE and Firefox | Tom | 2014-04-27 | 2014-04-27 | Ok
Q | Q2 | Blackbox | Integration | Edit User | Chrome, IE and Firefox | Tom | 2014-04-26 | 2014-04-27 | Ok
| Q3 | Blackbox | Integration | Add User | Chrome, IE and Firefox | Tom | 2014-04-26 | 2014-04-27 | Ok

## Fault_Summary Con02
Fault Summary
Date | Test No | Error | Issued to | Date Retested | OK?
2014-04-27 | Q3.1 Add User | First name, Last name and username allows special characters | Jenny | 2014-04-27 | OK | Jenny
2014-04-27 | Q3.2 Edit User | First name, Last name and username allows special characters | Jenny | 2014-04-27 | OK | Tom
2014-04-27 | G3.2 Edit Presenter | First name, Last name, organisation, medical field, position and qualification allows special characters | Jenny | 2014-04-27 | OK | Will
2014-04-24 | Q2.3 Add User | Password Validation acceptance error | Jenny | 2014-04-24 | OK
26/04/214 | E3.1 Step 04 | Requirements: Edit Conference link, is broken | Andy | 26/04/214 | OK
26/04/215 | E3.1 Step 09 | Interface: Bug: Dialog box comes up in the 'Clone Confirmation Area' when cancel is selected. This dialog box message "Copying Data, Please Wait", should not appear. | Andy | 26/04/215 | OK
26/04/216 | E3.1 Step 11 | Interface: On the Delete confirmation page for Conference a stray echo 'Array' above the Conference Table is seen. | Andy | 26/04/216 | OK