## Risks
Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2013-10-08 | Inaccurate Information from Client | Information gathered from the client may not accurately reflect the requirements they have for the system. This could be due to a misunderstanding during interviews, or the client not being completely sure about the requirements at the time of interview. | Indirect, Resource | 4 | 30% | 1.2 | Project Manager | The Project Manager will review all documentation with the client prior to development commencing to ensure that all information reflects the client's requests. | Newly Added Risk for Iteration 03
2 | 2013-10-11 | Lack of Required Skills | Due to the complexity of the project, it is possible that team members may not have all the required skills before the development phase commences. This could cause the budget to blow out, deadlines to be missed, and could potentially jeopardise the entire project. | Direct, Technical | 5 | 20% | 1 | Project Manager | The Project Manager will study the skills required for development of the system, and if necessary will arrange for team members to be trained prior to development commencing. | Added Construction 04
3 | 2014-05-01 | Non Adherance to functional requirements. | A failure from the developers to follow requirements set out in the functional requirements document | Direct Resource | 5 | 60% | 3 | Team | Take more care and maintain more rigid policies conforming to the requirements.
4 | 2013-10-11 | Faulty System Design | If the system design does not meet the client's requirements, then there may be conflicts during system development. | Direct, Technical | 5 | 15% | 0.75 | Systems Analyst | The Systems Analyst will review the system design and ensure that all requirements are met.
5 | 2014-06-12 | Testing | Validation, requirement and design specifications are not met. | Direct Resourse | 4 | 80% | 3.2 | Team | Robust testing and testicular fortitude becomes a must.
6 | 2013-10-11 | Lack of Staff Commitment | If team members are not committed to the project, then other people will have to take over tasks that they were not scheduled to work on so that the project will be completed by the deadline. | Indirect, Resource | 3 | 15% | 0.45 | Project Manager | The Project Manager will speak to the team and create a plan to ensure that if any team members do not complete work, the rest of the team will be able to complete it before the deadline.
7 | 2014-06-12 | High Turn over of project team | Creates extra work load as well as challenging scenerio | Indirect, Resource | 3 | 40% | 1.2 | Team | Improve team cohesion through proactive communication.
8 | 2014-06-12 | Insufficient time and human resource. | Project struggle under the load created around exam and assignment submition area. | Indirect, Resource | 3 | 0.1 | 0.3 | Team | Consider alternative implementation approaches or rescheduling and reprioritising work.
9 | 2014-06-12 | Poor Team Dynamics | Conflicts and stress created by sluggish response for unilateral planning. | Direct Resourse | 2 | 35% | 0.7 | Team | Involv interactive team management to identify issues and act as facilitator to resolve team issues.
10 | 2014-06-12 | Iteration Creep | As iterations draw to a close. Work that creeps from another iteration affects the coming iteraion before it starts. | Direct Resourse | 5 | 49% | 2.45 | Team | Consider alternative implementation approaches or rescheduling and reprioritising work.
11 | 2014-08-02 | Inadequate testing | Testing seems to be not done properly | Technical | 5 | 80% | 4 | Team | Consider using automated testing
12 | 2014-10-02 | Multiplatform failure | Multiplatform (PhoneGap) might have platform-specific issues (e.g. camera function works in Android but it doesn't work in iOS) | Technical | 5 | 80% | 4 | Team | Always use the latest version of PhoneGap
Note on E3: Risk Type = Direct or Indirect Resource Business Technical Schedule
Note on F3: Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G3: Probability is the percentage chance that a risk will occur.
Note on H3: Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.