## Web Team 1
Team 1
Functional Requirements for DSTC/Epworth eConference web application. |  |  |  |  | Use Case Specification |  |  | Programming |  |  |  | Testing |  |  |  | User & System Testing
Area | User Tasks | Feature | Priority | Points | Name | Assigned to | Date Completed | Program Name | Assigned to | % complete | Date Completed | Test Plan Number | Tested | Debugged | Retested ok | Completed By | System Test | Completed By | System Test
Conference | View conferences | Display a list of all conferences in a table format. | 1 | 1 |  | Will | 100% | conference.php | Andy | 100%
|  | Table is sorted (Conference date descending) | 1 |  |  |  |  | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
| Add a Conference | Add a new Conference | 1 | 1.5 | e-conference_Add_Conferences.docx | Will | 100% | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
| Delete a Conference | Delete an existing conference Conference -> | 3 | 1.5 | e-conference_Delete_Conferences.docx | Will | 100% | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
|  | Delete associated sessions | 3 |  |  |  |  | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
| Edit a Conference | Edit Conference details | 1 | 1.5 | e-Conference_Edit_Conferences.docx | Will | 100% | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
| Clone a Conference | Clone a conference and its sections-> a copy of an existing conference | 4 | 5 |  | Andy | 100% |  | Andy | [6 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
|  | Clone Sessions, speakers, sponsors etc | 4 |  |  |  |  | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
|  | Display a refreshed view of all Conferences after any changes are complete | 1 |  |  |  |  | conference.php | Andy | 100% | [5 empty] | Jenny | 2014-06-10 | Jack | 2014-08-01
Conference Section | View Sections | Select a conference from a list -> and then Display all conference sections in a table | 1 | 1 |  |  |  | view.php | Jenny | 100% | 2014-03-12 | F1 | 2014-03-19 |  |  | Will | 2014-06-10 | Jack | 2014-08-01
|  | Table is sorted (Alphabetical Ascending) | 1 |  |  |  |  | view.php | Jenny | 100% | 2014-03-12 | F1 |  |  |  | Will | 2014-06-10 | Jack | 2014-08-01
| Add a Conference Section | Add a new Conference Section | 1 | 2 |  |  |  | add.php | Jenny | 100% | 2014-03-12 | F2 | 2014-03-19 |  |  | Will | 2014-06-10 | Jack | 2014-08-01
| Delete a Conference Section | Delete an existing conference Conference Section-> | 3 | 1.5 |  |  |  | delete.php | Jenny | 100% | 2014-03-12 | F4 | 2014-03-19 |  |  | Will | 2014-06-10 | Jack | 2014-08-01
|  | Delete associated sessions (After confirmation) | 3 |  |  |  |  | delete.php | Jenny | 100% | 2014-03-12 | F4 |  |  |  | Will | 2014-06-10 | Jack | 2014-08-01
| Edit a Conference Section | Edit Conference Section details | 1 | 2 |  |  |  | edit.php | Jenny | 100% | 2014-03-12 | F3 | 2014-03-19 | 2014-03-20 | 2014-03-20 | Will | 2014-06-10 | Jack | 2014-08-01
|  | Display a refreshed view of all conference sections after any changes are complete | 1 |  |  |  |  | edit.php | Jenny | 100% | 2014-03-12 | F3
Session | View sessions | Select a conference from a list -> | 1 | 1 |  |  |  | view.php | Tom | 100% | 2014-03-14 | D1 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
|  | Display all sessions in a table format | 1 |  |  |  |  | view.php | Tom | 100% | 2014-03-14 | D1 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
|  | Table is sorted by date and time | 1 |  |  |  |  | view.php | Tom | 100% | 2014-03-14 | D1 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
| Add a session | Add a new session to the conference | 1 | 1.5 |  |  |  | add.php | Tom | 100% | 2014-03-14 | D2 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
|  | Assign a presenter (or presenters) to a session | 3 |  |  |  |  | add.php | Tom | 100% | 2014-03-14 | D2 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
| Delete a session | Delete a Session from a conference -> | 3 | 1.5 |  |  |  | delete.php | Tom | 100% | 2014-03-14 | D3 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
|  | Delete associated speakers for the session if they have no other sessions (after confirmation) | 4 |  |  |  |  | delete.php | Tom | 100% | 2014-03-14 | D3 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
| Edit a session | Edit a session | 3 | 2 | e-Conference_Edit_Session.docx | Will | 100% | edit.php | Tom | 100% | 2014-03-14 | D4 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
|  | Change the presenter (or presenters for a session) | 1 |  |  |  |  | edit.php | Tom | 100% | 2014-03-14 | D4 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
|  | Display a refreshed view of all sessions after any changes are complete | 1 |  |  |  |  | edit.php | Tom | 100% | 2014-03-14 | D4 | 2014-03-19 | N/A | N/A | Will | 2014-06-10 | Jack | 2014-08-01
Presenters | View Presenters | Select a conference from a list -> | 1 | 1 | e-Conference_Delete_Presenter_Profile.docx | Will | 100% | view.php | Will | 100% | 2014-03-18 | G1 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Paulo | 2014-08-01
|  | Table is sorted (Alphabetical Ascending on Last Name) | 1 |  |  |  |  | view.php | Will | 100% | 2014-03-18 | G1 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Paulo | 2014-08-01
| Add a Presenter | Add a Presenter and his/her bio details -> | 1 | 2 |  | Will | 100% | add.php | Will | 100% | 2014-03-18 | G2 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Paulo | 2014-08-01
|  | Assign the presenter to a session | 1 |  |  |  |  | add.php | Will | 100% | 2014-03-18 | G2 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Paulo | 2014-08-01
| Edit a Presenter | Edit a Presenter and his/her bio details including a photo | 1 | 2 | e-Conference_Edit_Presenter.docx | Will | 100% | edit.php | Jenny | 100% | 2014-04-17 | G1 | 2014-04-23 | N/A | N/A |  |  | Paulo | 2014-08-01
| Delete a Presenter | Delete a Presenter and his/her bio details including a photo | 3 | 1.5 | e-Conference_View_Presenter_Profile.docx | Will | 100% | delete.php | Jenny | 100% | 2014-04-17 | G2 | 2014-04-23 | N/A | N/A |  |  | Paulo | 2014-08-01
|  | Display a refreshed view of all presenters after any changes are complete | 1
[18 empty] | Rudhra | 2014-08-01
Sponsors | View Sponsors | Display a list of all sponsors in a table format. | 3 | 1 |  |  |  | view.php | Tom | 100% | 2014-05-22 | Z | 2014-05-22 | N/A | N/A |  |  | Rudhra | 2014-08-01
|  | Table is sorted (Alphabetical Ascending on sponsor name) | 3 | [14 empty] | Rudhra | 2014-08-01
| Add a Sponsor | Add a Sponsor's details (including logo) | 3 | 2 | e-conference_Add_Sponser.docx | Will | 100% | add.php | Tom | 100% | 2014-05-22 | Z | 2014-05-22 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Edit a Sponsor | Edit a Sponsor's details (including logo) | 3 | 2 |  |  |  | edit.php | Tom | 100% | 2014-05-22 | Z | 2014-05-22 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Delete a Sponsor | Delete a Sponsor's details (including related sponsorships (after confirmation) | 4 | 1.5 |  |  |  | delete.php | Tom | 100% | 2014-05-22 | Z | 2014-05-22 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Update Sponsorship | Assign the Sponsor to a conference (can sponsor many conferences) | 3 | 1.5 |  |  |  | index.php | Tom | 100% | 2014-05-22 | Z | 2014-05-22 | N/A | N/A |  |  | Rudhra | 2014-08-01
|  | Remove a Sponsorship of a conference | 3 | 1.5
|  | Display a refreshed view of all Sponsors after any changes are complete | 3
Venues | Manage Venues | Add a venue | 3 | 1 | e-Conference_Manage_Maps.docx | Shuhei | 100% | add.php | Shuhei | 100% | 30/08/2014 |  | 30/08/2014 | N/A |  | Rudhra | 30/08/2014
|  | Delete a venue | 3 | 1 |  |  | 100% | delete.php | Shuhei | 100% | 30/08/2014 |  | 30/08/2014 | N/A |  | Rudhra | 30/08/2014
|  | Edit a venue | 3 | 1 |  |  | 100% | view.php | Shuhei | 100% | 30/08/2014 |  | 30/08/2014 | N/A |  | Rudhra | 30/08/2014
|  | List available venues | 3 | 1
Trade Equipment | View Equipment | Display a list of all Trade Equipment in a table format. | 5 | 1
|  | Table is sorted (Equipment Name date descending) | 5
| Add Equipment | Add an item of Equipment | 5 | 1.5
| Delete Equipment | Delete an item of Equipment | 5 | 1.5
| Edit Equipment | Edit an item of Equipment | 5 | 1.5 | e-Conference_Edit_Equipment.docx | Will | 100%
|  | Refresh the view of all trade equipment Items | 5
Help System | Access Help | Open help screen from main page | 4 | 2
|  | Open help screen from any page | 4 | 3
|  | View documentation for specific page | 4
|  | View documentation for all pages | 5
|  | View walkthrough/tutorial for basic tasks | 5 | 3
|  | Search help screen | 5
Generating Report | Access Help | Generate a PDF report for Conferences | 5 | 2 |  |  |  | conference_report.php | Paulo | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Shuhei | 2014-08-30
|  | Generate a PDF report for Sections | 5 | 3 |  |  |  | section_report.php | Paulo | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Shuhei | 2014-08-30
|  | Generate a PDF report for Sessions | 5 |  |  |  |  | session_report.php | Paulo | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Shuhei | 2014-08-30
|  | Generate a PDF report for Questions | 5 |  |  |  |  | question_report.php | Paulo | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Shuhei | 2014-08-30
|  | Generate a PDF report for Polling | 5 | 3 |  |  |  | question_polling.php | Paulo | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Shuhei | 2014-08-30
|  | Generate a PDF report for Feedback | 5 |  |  |  |  | question_feedback.php | Paulo | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Shuhei | 2014-08-30
Separate admin login & member login | Access Help | Generate a PDF report for Conferences | 5 | 2 |  |  |  |  | Rudhra | 100% | 2014-08-29 |  | 2014-08-30 | N/A |  | Paulo | 2014-08-30
Functional Requirements for DSTC/Epworth eConference web service
Area | User Tasks | Feature | Priority
Conference | Initial Download | Download all data for that conference, including sessions presenters, Feedback Questions etc (Activated on first use of the conference code) | 1 | 5 |  |  |  | index.php | Tom | 100% | 2014-04-28 | U1 | 2014-04-24 | N/A | N/A |  |  | Jack | 2014-08-01
| Sync | Check for latest version of the data. If changes have been made, provide update to mobile app. | 3 |  |  |  |  | index.php | Tom | 100% | 2014-04-28 | U2 | 2014-04-25 | N/A | N/A |  |  | Jack | 2014-08-01
|  |  | Total Programming Points | 71.5
Team 2
Functional Requirements for DSTC/Epworth eConference web application.
Area | User Tasks | Feature | Priority | Programming Points
Home Page | Home Page | Brief Description of the System | 1 | 1.5 |  |  |  | home.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10 | Rudhra | 2014-08-01
|  | Login Panel embedded in Home Page | 1 |  |  |  |  | home.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10 | Rudhra | 2014-08-01
|  | Once logged in Users Name details are displayed along with a welcome. | 1 |  |  |  |  | home.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10 | Rudhra | 2014-08-01
|  | Navigation Bar is also attached | 1 |  |  |  |  | home.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10 | Rudhra | 2014-08-01
|  | Includes links to all other Admin Pages and contains suitable images | 1 |  |  |  |  | home.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10 | Rudhra | 2014-08-01
[12 empty] | C2 | 2014-05-21 | N/A | N/A
Navigation Bar (site wide element) | Navigate to | Present Main options | 1 | 1.5 |  |  |  | nav.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10
|  | Warn user of uncommited data on editor page before proceeding | 1 |  |  |  |  | menu.css | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10
|  | Present drop down submenu options: Speakers, maps, sponsors etc | 1 | [8 empty] | C3 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10
| Logout icon | End session and return to the login screen. | 1 |  |  |  |  | nav.php | Caue | 100% | 2014-05-20 | C1 | 2014-05-21 | N/A | N/A | Jenny | 2014-06-10
Users | View Users | Present a table of users | 2 | 1 |  |  |  | view.php | Jenny | 100% | 2014-04-16 | Q1 | 2014-04-24 | N/A | N/A | Tom | 2014-06-10 | Paulo | 2014-08-01
|  | Table is sorted | 2 | [8 empty] | Q2 | 2014-04-24 |  |  | Tom | 2014-06-10 | Paulo | 2014-08-01
| Add a User | Add a User | 2 | 2 |  |  |  | add.php | Jenny | 100% | 2014-04-18 | Q1 | 2014-04-24 | 2014-04-26 | 2014-04-27 | Tom | 2014-06-10 | Paulo | 2014-08-01
| Delete a User | Delete a User | 2 | 1.5 |  |  |  | delete.php | Jenny | 100% | 2014-04-18 | Q1 | 2014-04-24 | 2014-04-26 | 2014-04-27 | Tom | 2014-06-10 | Paulo | 2014-08-01
| Edit a User | Edit a User (Including change password - enforce complex password) | 2 | 1.5 |  |  |  | edit.php | Jenny | 100% | 2014-04-20 | Q1 | 2014-04-24 | N/A | N/A | Tom | 2014-06-10 | Paulo | 2014-08-01
|  | Passwords are encrypted | 2 | [12 empty] | Tom | 2014-06-10 | Paulo | 2014-08-01
| Reset Password | Reset Password | 2 | 1.5 |  |  |  |  | Andy | 0%
|  | Refresh the view. | 2 | [5 empty] | Andy | 0%
Polling | View Polling Questions | Select a conference from a list and then a session from a second list-> | 1 | 1 |  |  |  | view.php | Caue | 100% | 2014-05-20 | I1 | 2014-04-25 | N/A | N/A |  |  | Rudhra | 2014-08-01
|  | Display all polling questions in a Table format (sorted by Question number) | 1 | [8 empty] | I3 | 2014-04-25 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Add Polling Question | Add a Polling Question to a session | 1 | 2 |  |  |  | add.php | Caue | 100% | 2014-05-20 | I1 | 2014-04-25 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Delete Polling Question | Delete Polling Question from a session | 2 | 1.5 |  |  |  | delete.php | Caue | 100% | 2014-05-20 | I1 | 2014-04-25 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Edit a Polling Question | Edit a polling question | 1 | 2 |  |  |  | edit.php | Caue | 100% | 2014-05-20 | I1 | 2014-04-25 | N/A | N/A |  |  | Rudhra | 2014-08-01
| Link/un-link Polling Questions | Link an Existing polling question to a Session | 2 | 1.5 |  |  |  | edit.php | Caue | 100% | 2014-05-20 | I1 | 2014-04-25 | N/A | N/A |  |  | Rudhra | 2014-08-01
|  | Unlink an existing Polling question from a Session | 2
|  | Display a refreshed view of all polling Questions after any changes are complete | 1
| Manage Polling Availability | Open Polling for a session | 3 | 1.5 |  |  |  | avail.php | Shohei | 100% | 2014-05-22 | I | 2014-05-22 | N/A | N/A
|  | Close Polling for a session | 3
Note: a Polling question includes all options as well
Polling Results | Display Polling Results | Present a system to navigate to the desired session | 2 | 2 |  |  |  | result.php | Shohei | 100% | 2014-05-21 | J | 2014-04-26 | N/A | N/A
|  | List the question and a graph of polling results. (and move to next question if required) | 2
Feedback Forms | View Conference Feedback forms | Display all conferences in a table format -> Select feedback link | 2 |  | View Feedback Form.docx | Shohei | 100% | view.php | Shohei | 100% | 2014-05-18 | K | 2014-04-26 | N/A | N/A | Tom | 2014-06-10 | Shuhei | 2014-08-01
|  | Display Conference Feedback form including its sections (many of these) | 2 | [12 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
| Add a feedback form | Create a new feedback form together with its sections | 2 |  | Add Feedback Form.docx | Shohei | 100% | add_f.php/add_s.php | Shohei | 100% | 2014-05-18 | K | 2014-04-26 | N/A | N/A | Tom | 2014-06-10 | Shuhei | 2014-08-01
| Edit a feedback form | Edit an existing feedback form together with its sections | 2 | 1.5 |  |  |  | edit_f.php/edit_s.php | Shohei | 100% | 2014-05-18 | K | 2014-04-26 | N/A | N/A | Tom | 2014-06-10 | Shuhei | 2014-08-01
| Delete a Feedback Form | Delete an existing feedback form together with its sections (after confirmation) | 3 | 1.5 |  |  |  | delete_f.php/delete_s.php | Shohei | 100% | 2014-05-18 | K | 2014-04-26 | N/A | N/A | Tom | 2014-06-10 | Shuhei | 2014-08-01
| View Conference Feedback forms (specific user) | Display updated Conference feedback for after changes are complete. The feedbacks of the conference which the user is related will be only accessible to that user. | 2 |  |  |  |  | view.php | Rudhra | 100% | 26/09/2014 | K | 26/09/2014 | N/A | N/A | Shuhei | 28/09/2014 | Shuhei | 28/09/2014
Q & A | Review Questions | View all questions submitted. | 2 | 1 |  |  |  |  | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
|  | Remove duplicate or inappropriate questions. | 2 | 1 |  |  |  |  | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
|  | Sort the questions from the most important to least important. | 2 | [5 empty] | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
|  | Selects which questions the speaker will view and answer. | 2 | 1 |  |  |  |  | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
|  | Highlight selected question | 2 | [5 empty] | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
|  | Presenter can view questions after they have been reviewed. | 2 | 1 |  |  |  |  | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
| RSS Feed | Provide RSS feed for Mobile app (Questions that have been selected) | 3 | 2 |  |  |  |  | William | 100% | [5 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
[16 empty] | Tom | 2014-06-10 | Shuhei | 2014-08-01
Login/Security | User login | Check UserId and Password and allow access when correct | 3 | 2 |  |  |  |  | Andy | 100%
|  | Conference Administrators gain access to their Conference data | 3 | [5 empty] | Andy | 0%
|  | Test connection to database, report error if connectivity problem | 3 | [5 empty] | Andy | 100%
|  | Enter a username and password | 3 | [5 empty] | Andy | 100%
|  | Submit login info to database, report if login details incorrect | 3 | [5 empty] | Andy | 100%
|  | All Web Pages must check that the user is logged on and authenticated. | 3 | 2 |  |  |  |  | Andy | 0%
|  | Reset password at log in | [6 empty] | Jenny | 80%
Feedback Questions | View Feedback Questions | Select a conference from a list -> | 3 | 1 |  |  |  | view.php | Shohei | 100% | 2014-05-20 | 6 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Shuhei | 2014-08-01
|  | Display all feedback questions from that conference in a table format | 3 | [12 empty] | Will | 2014-06-10 | Shuhei | 2014-08-01
| Add Feedback Question | If the Question is for a session select the session name from a list of sessions | 3 | 2 |  |  |  | add.php | Shohei | 100% | 2014-05-20 | 6 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Shuhei | 2014-08-01
|  | Add a multi-choice feedback question to a conference section. | 3 | [12 empty] | Will | 2014-06-10 | Shuhei | 2014-08-01
|  | Add a text response feedback question to a conference section. | 3 | 0.5 | [11 empty] | Will | 2014-06-10 | Shuhei | 2014-08-01
| Delete Feedback Question | Delete Feedback Question from a session (after verification from the user) | 4 | 1.5 |  |  |  | delete.php | Shohei | 100% | 2014-05-20 | 6 | 2014-03-21 | N/A | N/A | Will | 2014-06-10 | Shuhei | 2014-08-01
| Edit a Feedback Question | Edit a Feedback question | 3 | 2 |  |  |  | edit.php | Shohei | 100% | 2014-05-20 | L | 26.04/2014 | N/A | N/A | Will | 2014-06-10 | Shuhei | 2014-08-01
| Link/un-link Feedback Questions | Link an Existing Feedback question to a Conference/Session | 4 | 1.5 | [11 empty] | Will | 2014-06-10 | Shuhei | 2014-08-01
|  | Unlink an existing Feedback question from a Conference/Session | 4 | [12 empty] | Will | 2014-06-10 | Shuhei | 2014-08-01
|  | Display a refreshed view of all Feedback Questions after any changes are complete | 3
| View Conference Feedback forms (specific user) | Display updated questions. The questions which the user is related will be only accessible to that user. | 2 |  |  |  |  | view.php | Rudhra | 100% | 26/09/2014 | K | 26/09/2014 | N/A | N/A | Shuhei | 28/09/2014 | Shuhei | 28/09/2014
Note: a Feedback question includes all options as well
Reports | Polling Results | Print a high quality PDF report of the results of the all polling questions for a session | 4 | 3 |  |  |  | pdf.php | Caue | 50% | 2014-04-25 | N/A | N/A | N/A | N/A
| Feedback Questions | Print a high quality report of the Feedback questions and results (Including Graphs) | 4 | 3 |  |  |  | pdf.php | Caue | 50% | 2014-04-25 | N/A | N/A | N/A | N/A
| Q & A | Print a high quality report of the Q & A questions | 4 | 2 |  |  |  |  | Caue | 0% |  | N/A | N/A | N/A | N/A
Attendee Profile | View Attendee Profiles | Present a table of attendee profiles | 3 |  | e-Conference_Add_Attendee_Profile.docx | Tom | 2014-04-23 | view.php | Caue | 100% | 2014-03-15 | Test5 | 2014-03-20 | N/A | N/A
|  | Table is sorted | 3
| Add a Attendee Profile | Add a new Attendee Profile | 3 |  | e-Conference_View_Attendee_Profile.docx | Tom | 2014-04-23 | add.php | Caue | 100% | 2014-03-15 | Test5 | 2014-03-20 | N/A | N/A
| Delete a Attendee Profile | Delete an attendee Profile (After Confirmation) | 3 | 1.5 |  |  |  | delete.php | Caue | 100% | 2014-03-15 | Test5 | 2014-03-20 | N/A | N/A
| Edit a Attendee Profile | Edit an attendee Profile | 3 | 1.5 |  |  |  | edit.php | Caue | 100% | 2014-03-15 | Test5 | 2014-03-20 | N/A | N/A
|  | Refresh the view | 3
Functional Requirements for DSTC/Epworth eConference web service
Area | User Tasks | Feature | Priority
Polling | Accept Polling data | Accept polling and attendee profile data from mobile app | 2 | 3 |  |  |  | index.php | Tom | 100% | 2014-04-25 | V1 | 2014-04-25 | N/A | N/A
|  | Check if polling is still open on the session | 2
|  | Store the data in the database | 2
Q & A | Accept upload of Q & A | Accept Q & A questions and profile data from attendees. | 3 | 3 |  |  |  | index.php | Will | 100% | 2014-04-25 | W | 2014-04-25 | N/A | N/A
|  | Save the Questions and profile Id in the database | 3
Feedback | Accept upload of Feedback Answers | Accept feedback answers and profile ID from attendees. | 4 |  |  |  |  | index.php | Will | 100% | 2014-04-25 | X | 2014-04-25 | N/A | N/A
|  | Save the answers and profile data in the database | 4 | 3
Log in | Mobile user log in details | Accept credentials entered by user. | [5 empty] | index.php | Tom | 100% | 2014-05-22 | Z | 2014-05-23 | N/A | N/A
Transfer images | Allow user to request for particular images | Accept id of image requested | [5 empty] | index.php | Tom | 100% | 2014-05-22 | Z | 2014-05-23 | N/A | N/A
|  |  | Total Programming Points |  | 0